## Sheet1
Task | Tangga Mulai | Tanggal Selesai | Nama Developer | Status
Prepocessing Data | 2021-10-23 | 2021-10-23 | Aries | Done
Modelling CNN | 2021-10-25 | 2021-11-02 | Jody | Done
Modelling CNN with overfiting handiling | 2021-11-08 | 2021-11-09 | Jody | Done
Modelling Alexnet and Densenet201 | 2021-11-09 | 2021-12-04 | Jody | Done
Model Deploymet | 2021-12-15 | 2021-12-28 | Aries | On Going